## Sheet1
monthly operational Report
Supervisor | Innocent Kaseko
Start | 2022-02-01
| Task Description | Start Date | Planned End Date | Working Days
| Entrance management system Frontend | 2022-02-01 | 2022-02-08 | 6
| Complete Requirements Gathering | 2022-02-01 | 2022-02-02
| Frontend designing | 2022-02-03 | 2022-02-05
| Frontend Functionality intergration | 2022-02-06 | 2022-02-08
| sales real time dashboard power -bi and bing maps for geo- location | 2022-02-09 | 2022-02-15 | 5
| Setting Power Bi Environments( Desktop App and web service | 2022-02-09 | 2022-02-09
| Converting commercial reports made in excel to power bi (testing purposes) | 2022-02-09 | 2022-02-14
| Publishing desktop Power Bi reports to Power Bi web Service | 2022-02-14 | 2022-02-15
| Entrance management system Backend | 2022-02-16 | on-going | on-going
| Backend designing | 2022-02-16 | 2022-02-18
| Development | 2022-02-21 | 2022-02-25
| Development | 2022-02-28 | on-going